## Team Backlog
Team Backlog
Task Name | Assignee | Task Status | Expected Time to Finish (Hrs) | Actual Time to Finish (Hrs)
Design
High Level Design
Layered Architecture | All Team | Done | 2 | 2
Project Circuit Schematic | Tarek | Done | 2 | 1
Modules' Description | Tarek | Done | 2 | 1
Drivers' Documentation | Hossam | Done | 2 | 4
Low Level Design
Functions' Flowchart | All Team | Done | 7 | 6
Summary
Document File | Hossam | Done | 2 | 3
Implementation
MCAL Module
DIO Driver | Hossam | Done | 4 | 3
EXI Driver | Abdelrhman | Done | 3 | 1.5
TMR Driver | Mahmoud | Done | 8 | 9
HAL Module
LED Driver | Hossam | Done | 2 | 1.5
BTN Driver | Abdelrhman | Done | 2 | 1
DCM Driver | Mahmoud | Done | 7 | 2
APP Module
APP Module | Abdelrhman & Hossam | Done | 6 | 4
Testing
Documentation
Test Protocol Excel Sheet | All Team | Done | 3 | 2
Unit Testing
Test MCAL | All Team | Done | 3 | 1.5
Test HAL | All Team | Done | 4 | 3
System Testing
Test APP | All Team | Done | 4 | 6
Final Requirements Review | All Team | Done | 2 | 1
Video
Video Recording | All Team | Done | 4 | 1
Video Editing | Abdelrhman & Hossam | Done | 3 | 1

## Test Protocol
Test Protocol
Test Case ID | Test Case Description | Test Case Steps | Expected Result | Actual Result | Pass/Fail
MCAL Module
DIO Driver
TC_DIO_001 | Test DIO initialization | 1. Call DIO_init with valid parameters | EN_DIO_Error_T is returned as DIO_OK | Matches Expected Result | Pass
TC_DIO_002 | Test DIO read | 1. Call DIO_init with valid parameters 2. Call DIO_write with a value of 1 3. Call DIO_read | u8_a_value is returned as 1 | Matches Expected Result | Pass
TC_DIO_003 | Test DIO write | 1. Call DIO_init with valid parameters 2. Call DIO_write with a value of 1 | EN_DIO_Error_T is returned as DIO_OK | Matches Expected Result | Pass
TC_DIO_004 | Test DIO toggle | 1. Call DIO_init with valid parameters 2. Call DIO_write with a value of 1 3. Call DIO_toggle 4. Call DIO_read | u8_a_value is returned as 0 | Matches Expected Result | Pass
TC_DIO_005 | Test port initialization | 1. Call DIO_portInit with valid parameters | EN_DIO_Error_T is returned as DIO_OK | Matches Expected Result | Pass
TC_DIO_006 | Test port write | 1. Call DIO_portInit with valid parameters 2. Call DIO_portWrite with a value of 0x55 and a mask of 0xFF (DIO_NO_MASK) | The specified port pins are set to 0x55 | Matches Expected Result | Pass
TC_DIO_007 | Test port toggle | 1. Call DIO_portInit with valid parameters 2. Call DIO_portWrite with a value of 0x55 and a mask of 0xFF (DIO_NO_MASK) 3. Call DIO_portToggle with a mask of 0xFF (DIO_NO_MASK) 4. Call DIO_portWrite with a value of 0xAA and a mask of 0xFF (DIO_NO_MASK) 5. Call DIO_portToggle with a mask of 0xFF (DIO_NO_MASK) | The specified port pins are toggled between 0x55 and 0xAA | Matches Expected Result | Pass
TC_DIO_008 | Re-Test with invalid data | Re-test cases from 1 to 7 with invalid data | Return DIO_ERROR | Matches Expected Result | Pass
EXI Driver
TC_EXI_001 | Test EXI enablePIE | 1. Call EXI_enablePIE with valid parameters (Correct interruptId and senseControl) | STD_OK is returned as u8 errorState | Matches Expected Result | Pass
TC_EXI_002 | Test EXI enablePIE | 1. Call EXI_enablePIE with invalid parameters (Incorrect interruptId or senseControl) | STD_NOK is returned as u8 errorState | Matches Expected Result | Pass
TC_EXI_003 | Test EXI disablePIE | 1. Call EXI_disablePIE with valid parameters (Correct interruptId) | STD_OK is returned as u8 errorState | Matches Expected Result | Pass
TC_EXI_004 | Test EXI disablePIE | 1. Call EXI_disablePIE with invalid parameters (Incorrect interruptId) | STD_NOK is returned as u8 errorState | Matches Expected Result | Pass
TC_EXI_005 | Test EXI intSetCallBack | 1. Call EXI_intSetCallBack with valid parameters (Correct interruptId and Valid Pointer) | STD_OK is returned as u8 errorState | Matches Expected Result | Pass
TC_EXI_006 | Test EXI intSetCallBack | 1. Call EXI_intSetCallBack with invalid parameters (Incorrect interruptId or Null Pointer) | STD_NOK is returned as u8 errorState | Matches Expected Result | Pass
TIMER Driver
TC_TIMER_001 | Test timer0 & timer2 Init | 1. Call TMR_timer0NormalModeInit & TMR_timer2NormalModeInit | The two timers working in the normal mode | Matches Expected Result | Pass
TC_TIMER_002 | Test timer0 delay function | 1. Call TMR_timer2Delay with deferent delay ranges | The desired delay is acheived | Matches Expected Result | Pass
TC_TIMER_003 | Test timer2 delay function | 1. Call TMR_timer0Delay with deferent delay ranges | The desired delay is acheived | Matches Expected Result | Pass
TC_TIMER_004 | Test timer0 & timer2 start | 1. Call TMR_timer0Start & TMR_timer2Start | The two timers start working in normal mode | Matches Expected Result | Pass
HAL Module
LED Driver
TC_LED_001 | Test LED initialization | 1. Call LED_init with valid parameters | EN_LED_ERROR_t is returned as LED_OK | Matches Expected Result | Pass
TC_LED_002 | Test LED on | 1. Call LED_init with valid parameters 2. Call LED_on | EN_LED_ERROR_t is returned as LED_OK and the LED is turned on | Matches Expected Result | Pass
TC_LED_003 | Test LED off | 1. Call LED_init with valid parameters 2. Call LED_on 3. Call LED_off | EN_LED_ERROR_t is returned as LED_OK and the LED is turned off | Matches Expected Result | Pass
TC_LED_004 | Test LED array initialization | 1. Call LED_arrayInit with valid parameters | EN_LED_ERROR_t is returned as LED_OK | Matches Expected Result | Pass
TC_LED_005 | Test LED array on | 1. Call LED_arrayInit with valid parameters 2. Call LED_arrayOn with a mask of 0xFF (DIO_NO_MASK) | The specified LEDs are turned on and EN_LED_ERROR_t is returned as LED_OK | Matches Expected Result | Pass
TC_LED_006 | Verify that LED_arrayOff() function turns off all LEDs on a specific port when given a mask of DIO_NO_MASK. | 1. Initialize all LED pins on a specific port using LED_arrayInit() function. 2. Turn on all LEDs on the same port using LED_arrayOn() function and a mask of DIO_MASK_ALL. 3. Call LED_arrayOff() function with the same LED port and a mask of DIO_MASK_ALL. 4. Read the value of all LED pins on the same port using DIO_read() function. 5. Verify that all LED pins on the same port are turned off by checking that the value read in step 4 is 0x00. | All LED pins on the specified port should be turned off. | Matches Expected Result | Pass
TC_LED_007 | Re-Test with invalid data | Re-test cases from 1 to 6 with invalid data | Return LED_ERROR | Matches Expected Result | Pass
BTN Driver
TC_BTN_001 | Test BTN_init | 1. Call the BTN_init passing the button configuration | Btn pins are set as inputs, enabling pullup resistor | Matches Expected Result | Pass
TC_BTN_002 | BTN_getBtnState | 1. Call the BTN_getState passing btnId and pointer to the returned btnState (Correct parameters) | STD_OK is returned as u8 errorState | Matches Expected Result | Pass
TC_BTN_003 | BTN_getBtnState | 1. Call the BTN_getState passing btnId and pointer to the returned btnState (Incorrect parameters) | STD_NOK is returned as u8 errorState | Matches Expected Result
DCM Driver
TC_DCM_001 | Test DCM_init | 1. Call the DCM_init with passing the motor configuration's pointer | The output pins for motors are initialized | Matches Expected Result | Pass
TC_DCM_002 | TEST DCM_changeDirestion | 1. Call the DCM_changeDirection with passing the motor configuration's pointer & its ID | The motor's direction should be changed | Matches Expected Result | Pass
TC_DCM_003 | Test DCM_setDutyCycle | 1. Call the DCM_setDutyCycle with passing the required duty cycle | The motor's duty cycle should be configured | Matches Expected Result | Pass
APP Module
TC_APP_001 | Test APP_startProgram | Run the project in its Normal mode. | The default flow of the application. | Matches Expected Result | Pass
TC_APP_002 | Test APP_startProgram | Run the project, while trying to use the Stop Button. | The car stops and the red LED turns on. | Matches Expected Result | Pass
TC_APP_003 | Test APP_startProgram | Run the project, while trying to use the Start Button again during application flow. | Nothing happens. | Matches Expected Result | Pass
TC_APP_004 | Test APP_startProgram | Run the project, while trying to double press the Stop Button. | Nothing happens. | Matches Expected Result | Pass
TC_APP_005 | Test APP_startProgram | Run the project, while trying to double press the Start Button. | Nothing happens. | Matches Expected Result | Pass