## Team Backlog
Team Backlog |  |  |  |  | Hacker Kermit Team
Task Name | Assignee | Task Status | Expected Time to Finish (Hrs) | Actual Time to Finish (Hrs)
Design
High Level Design
Layered Architecture | All Team | Done | 2 | 2
Project Circuit Schematic | Tarek | Done | 2 | 1
Modules' Description | Tarek | Done | 2 | 1
Drivers' Documentation | Hossam | Done | 2 | 4
Low Level Design
Functions' Flowchart | All Team | Done | 7 | 6
Summary
Document File | Hossam | Done | 2 | 3
Implementation
MCAL Module
DIO Driver | Hossam | Done | 4 | 3
EXI Driver | Abdelrhman | Done | 3 | 1.5
TMR Driver | Mahmoud | Done | 8 | 9
HAL Module
LED Driver | Hossam | Done | 2 | 1.5
BTN Driver | Abdelrhman | Done | 2 | 1
DCM Driver | Mahmoud | Done | 7 | 2
APP Module
APP Module | Abdelrhman & Hossam | Done | 6 | 4
Testing
Documentation
Test Protocol Excel Sheet | All Team | Done | 3 | 2
Unit Testing
Test MCAL | All Team | Done | 3 | 1.5
Test HAL | All Team | Done | 4 | 3
System Testing
Test APP | All Team | Done | 4 | 6
Final Requirements Review | All Team | Done | 2 | 1
Video
Video Recording | All Team | Done | 4 | 1
Video Editing | Abdelrhman & Hossam | Done | 3 | 1